|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **16/01/2023 -> 27/01/2023** | | | | | | | | | | | |
| **Weeks** | **16** | **17** | **18** | **19** | **20** | **20 afternoons** | **23** | **24** | **25** | **26** | **27** | **27 afternoons** |
| **General Activity** | Red Blister measurements following protocols P&I and C&P | | | | | Send data +  Discussion with TRIKI | Tree selection for the CBB protocol (Select: 5 L2 shaded/ 5 L2 nonshaded/ 5 L3 shaded/ 5 L3 nonshaded + send map of selected trees | | CBB measurements on selected trees | | | Send data +Discussion with TRIKI |

# **Weekly activities and objectives:**

1. Measure the Red Blister on the selected in past season trees by following the protocols attached (P&I and C&P experiments).
2. Selecting the trees for the CBB and send the map of selected trees.
3. Measure the CBB on the previously selected trees by following the protocols attached (P&I and C&P experiments).